## Play area inspection checklist
Inspection Date: 08.10.21 |  | Inspection Time: 6.00 pm
Inspected By: Anne Ogilvie
Area/details | ü/ × | Issues/actions required | Logged on action list
Play area surrounds
Litter bins
Complete, undamaged | ü
Securely fixed against movement | ü
Not full/overflowing | ü
Accessible | ü
Seating
Undamaged, good condition | ü
Signage
Present, legible, securely fixed | ü
Fences
Undamaged, secure | ü
Paths
Undamaged, clear from obstructions | ü
Car park
Barriers - present, undamaged | ü
Surface - good condition | x | Glass still there | 2020-10-30
Trees
Undamaged, secure | ü
Old Play Area
Site
Grass cut | ü
No litter, glass, sharp objects | ü
Free from trip hazards | ü
Free from animal fouling | ü
No vegetation overhanging equipment | ü
Adequate site drainage | ü
Swings - one bay - two cradle
Supports present, secure, free from decay at ground level | ü
Metalwork undamaged, free from corrosion | ü
Working correctly, no undue noise | ü
Chains intact, good condition, less than 40% wear | ü
Seats unbroken, no exposed metal | ü
Seats fixed securely | ü
Grass surface: level, no trip hazards | ü
Agility Trail
Undamaged, secure | ü | Note - two rotten stillts have been removed by contractor | 2021-10-08
Grass surface: level, no trip hazards | ü
Toddler bridge
Stable, secure | x | Bridge has been removed as contractor could not resecure into ground due to rot | 2021-10-08
No protuding bolts or parts | ü
Grass surface: level, no trip hazards | ü | Ground made good by contractor | 2021-10-08
Carousel
Undamaged, level | ü
No protuding bolts or parts | ü
Revolves smoothly, noiselessly | ü
Clear of rubbish underneath | ü
Safety surface: undamaged, fixed securely, no undue gaps | ü
Safety surface: level with surrounding ground, no trip hazards | ü
Safety surface: free from weeds | ü
Multiplay toddler with slide
Undamaged, level | ü
No protruding bolts or parts | ü
Clear of rubbish underneath | ü
Surface at end of slide clear, level | ü
Grass surface: level, no trip hazards | ü
Rocker horse
Stable, secure | ü
Surface undamaged | x | Hole/depression in surface | 2021-07-21
No protruding bolts or parts | ü
Moves smoothly, noiselessly | ü
Grass surface: level, no trip hazards | ü
Rocker platform
Stable, secure | ü
No protruding bolts or parts | ü
Moves smoothly, noiselessly | ü
Grass surface: level, no trip hazards | ü
Rotator
Stable, secure | ü
No protruding bolts or parts | ü
Moves smoothly, noiselessly | ü
Safety surface: undamaged, fixed securely, no undue gaps | ü
Safety surface: level with surrounding ground, no trip hazards | ü
Safety surface: free from weeds | ü
Multiplay with slide
Undamaged, level | x | End part of slide is damaged | 2021-08-06
No protruding bolts or parts | ü
Clear of rubbis underneath | ü
Surface at end of slide clear, level | ü
Grass surface: level, no trip hazards | ü
New Play Area
Site
Grass cut | ü
No litter, glass, sharp objects | ü
Free from trip hazards | ü
Free from animal fouling | ü
No vegetation overhanging equipment | ü
Adequate site drainage | ü
Swings - pentagon - five seats
Supports present, secure, free from decay at ground level | ü
Metalwork undamaged, free from corrosion | ü
Working correctly, no undue noise | ü
Chains intact, good condition, less than 40% wear | ü
Seats unbroken, no exposed metal | ü
Seats fixed securely | ü
Safety surface: undamaged, fixed securely, no undue gaps | ü
Safety surface: level with surrounding ground, no trip hazards | ü
Safety surface: free from weeds | ü
Swings - basket
Supports present, secure, free from decay at ground level | ü
Metalwork undamaged, free from corrosion | ü
Working correctly, no undue noise | ü
Chains intact, good condition, less than 40% wear | ü
Seat unbroken, no exposed metal | ü
Seat fixed securely | ü
Safety surface: undamaged, fixed securely, no undue gaps | ü
Safety surface: level with surrounding ground, no trip hazards | ü
Safety surface: free from weeds | ü
Climber - web
Undamaged, level | ü
Stable, secure | ü
No protuding bolts or parts | ü
Moves smoothly, noiselessly | ü
Clear of rubbish underneath | ü
Safety surface: undamaged, fixed securely, no undue gaps | ü
Safety surface: level with surrounding ground, no trip hazards | ü
Safety surface: free from weeds | ü
Multiplay
Undamaged, level | ü
No protruding bolts or parts | ü
Clear of rubbish underneath | ü
Safety surface: undamaged, fixed securely, no undue gaps | ü
Safety surface: level with surrounding ground, no trip hazards | ü
Safety surface: free from weeds | x | Moss | 2020-10-30
Shelter
Undamaged, secure | ü
Free from litter | ü
Skate Park
Surface: undamaged | ü
Safety rails: secure, undamaged | ü
Driveway | ü
Flat bank | ü
Grind rail | ü
Skate-quarter pipe | ü
Any other observations
Some areas of safety surface are suffering from weed encroachment.
Toddler swing seats in need of cleaning